## Sheet1
			Estimated			Actual			April		April		April		April		April		April		April		April		April		April		April		April		April		April		April		April		April		April		April		April		April		May		May		May		May		May		May		May		May		May		May		May		May		May		May		May		May		May		May		May		May		May		May		May		June		June		June		June		June		June		June		June		June		June		June		June		June		June		June		June		June		June		June		June		June
Tasks	Sub-tasks	Sub-tasks	effort			effort			2		3		4		5		6		9		10		11		12		13		16		17		18		19		20		23		24		25		26		27		30		1		2		3		4		7		8		9		10		11		14		15		16		17		18		21		22		23		24		25		28		29		30		31		1		4		5		6		7		8		11		12		13		14		15		18		19		20		21		22		25		26		27		28		29
			(days)			(days)			M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F	M	F
Store existing report-type definitions and text in Berkeley DBs					29			0
	Identify (reverse-engineer) all report-type and meta report web-page variation from Perl scripts and website			15			0
	Define report-types in XML to be read in			1			0
	Put together an XML Schema for validation			1			0
	Define metadata tags for use in Berkeley DBs.			1			0
	Identify primary indexes needed for different groups of data			1			0
	Identify secondary indexes			1			0
	Write Report-type Update module to read and store report-content in Berkeley DB			9			0
		Read XML using XML parser from file or GUI	2			0
		Store in Berkeley DB using appropriate metadata	2			0
		Retrieve from Berkeley DB report-type definitions and text and display in GUI (initially for development)	5			0
Store new daily count data in Berkeley DBs					5			0
	Remove code from existing Usage report system that stores unwanted duplicate count data			1			0
	Remove code from existing Usage report system that stores customer/document data			1			0
	Modify code in Usage report system to store count data in cleaned-up format			3			0
Store updated state of Customer data in Berkeley DBs each month for report generation (Customer Update module)					3
	Identify primary and secondary indexes			1			0
	Read Customer data from Wispers database dump			1			0
	Write updated customer data to Berkeley DB at end of month			1			0
Store updated state of Document data in Berkeley DBs each month for report generation (Document Update module)					3			0
	Identify primary and secondary indexes			1			0
	Read Document data from Wispers database dump			1			0
	Write updated document data to Berkeley DB at end of month			1			0
Enable count data in original format to be accessed for usage reports					2			0
	Rerun counting for end-of-month for each of first few months of the current year for year-to-date reports			1			0
	Provide link for usage reports prior to current year (2007) to use old scripts			1			0
Report generation					7			0
	Write part of Report Generation module that, given a report request, will extract all relevant report-content.			3			0
	Identify and define the semantic XHTML tags to be used with div and span for CSS			1			0
		Sort semantic inline XHTML tags in Berkeley DB	0.25				0
		Investigate tables rows cols in CSS	0.25				0
		List main tags	0.5				0
	Write formatter part of Report Generation module that will produce the report in the appropriate formats - XHTML, CSV			3			0
Access control					4			0
	Write module to "release" reports (with GUI interface?)			1			0
	Implement interface to authentication mechanisms			1			0
	Write module to maintain list of privileged users (with GUI interface?)			2			0
Interface to Wiley Interscience					8			0
	Write top-level XSL (or XML with XInclude) file to integrate usage reports with boilerplate			2			0
	For an XSL file, use XSLT engine (Cocoon or Xalan), otherwise set up an XInclude processor			2			0
	Set up means of maintaining up-to-date Wiley Interscience boilerplate			1			0
	Write specific Usage Reporting CSS file			2			0
	Set up means of maintaining up-to-date Wiley Interscience CSS			1			0
Interface to webserver					3			0
	Set up Servlet or Cocoon sitemap to respond to webserver request			3			0
TOTAL					64			0